## Dispensation Pro Forma
OGA Inspection Finding Database
Table 1 - Open Findings | [5 empty] | Table 2 - Closed Findings
Inspection Finding Reference | Measurement System | Category | Date for Completion | Status | Days Remaining | Inspection Finding Reference | Measurement System | Category | Date for Completion | Date Closed | Status | Days Overdue
|  |  | dd/mm/yy | [5 empty] | dd/mm/yy | dd/mm/yy
INSTALLATION-2014-01 | oil export | 1a | 2014-02-28 | OVERDUE | -461 | INSTALLATION-2013-01 | oil export | 1a | 2014-02-28 | 2014-02-14 | ON TIME | -14
[6 empty] | INSTALLATION-2013-02 | gas export | 2a | 2013-12-31 | 2014-01-15 | OVERDUE | 15
Notes: | [5 empty] | Notes:
(1) Columns A-D should be completed with the inspection finding data. | [5 empty] | (4) Columns H-L should be completed with the data for closed inspection findings.
(2) For each row completed, the relevant cells in colums E-F should be copied, | [5 empty] | (5) For each row completed, colums M-L should be copied, to indicate whether actions were completed on time.
to indicate status of remedial action.
(3) When the dispensation is closed, data should be transferred from Table 1 to Table 2.
(see Notes 4-5).
Formulas:
Status = IF(TODAY()>[Date for Completion],"OVERDUE","OPEN")
Days Remaining = -(TODAY()-[Date for Completion])