## Attach 1 Scheme overview
Blue Hydrogen Production
350 MW – Train 2
New Blue hydrogen plant
Grid connections
or PPA?
Water
Desalination Unit
(SNS) CCUS
1-3 Mt/yr storage
onshore
pipeline
MW
offshore
pipeline
injection equipment - subsea or surface
Hydrogen pipeline(s)
Terminal point
Fiscal meeting?
Seawater Inlet
Brine discharg
Blue Hydrogen Production
Train - one unit or
multiple units
Steam?
Potable water?
Onshore/offshore booster compression
Terminal point
Fiscal meeting?
Control & automation for C02 & H2
including links to NTS and existing DCS or similar
Rail loading facility ?
Shell/BBL
Gas terminal
Internconnector
Condensate
BPA pipelines
National Grid
NTS
Export pipeline?
Gas
separation
Gas
separation
ENI Gas terminal
Disinvesment significantly advanced
Perenco
Gas terminal
Interconnector
C02?
separation
Repurpose scope facility

## Attach 2Work packages
Work Package | Supply chain | Type | Supply chain risk | Perceived Supply chain risk | Perceived risk - Long lead/schedule critical | Local | Regional | National |  |  | Market Participants
Engineering & Consulants | [8 empty] | Conditional formatting scale
Existing asset resuse study | Mature | Consultant | Capacity | ? | High | 5 | 5 | 26 |  | High Risk | 0 | 5
PreFEED/FEED | Mature | Contractor | Capacity | High | High | 5 | 5 | 26 |  | Medium Risk | 6 | 15
EPC/EPCM | Mature | Contractor | Capacity | High | High | 5 | 5 | 26 |  | Low Risk | 15 | 100
Planning (for DCO) | Mature | Consultant | Capacity | Low | High | 2 | 2 | 5
Permitting (for EA) | Mature | Consultant | Capacity | Low | High | 10 | 10 | 30
Legal | Mature | Consultant | Capacity | Low | Medium | 0 | 0 | 82
Funding/financial | Mature | Consultant | Capacity | Low | TBC | 0 | 0 | 82
OE | Mature | Consultant | Capacity | Low | Low
Modification to existing site(s)
Site clearance | [9 empty] | Proserv look like they should be on core group
Decommissioning, Disinvestment | Mature | Contractor | Capacity | Low | Low | 12 | 12 | 57
Dismantle & Demolition | Mature | Contractor | Capacity | Low | Low | 12 | 12 | 57
Integration
Control & automation | Mature | Contractor | Capacity | TBC | TBC | 3 | 3 | 71
Process connections | Mature | Contractor | Capacity | TBC | TBC | 4 | 4 | 31
Utilities - Fire, Drains, etc | Mature | Contractor | Capacity | Low | TBC | 6 | 6 | 35
H2 Bacton - new build
OSBL - Main packages
HV supply (MW from Grid) | Mature | Utility | Grid connection | High | High | 2 | 2 | 62
Desalination plant | Mature | OEM | Capacity | Medium | High | 0 | 0 | 4
Steam supply? | ? | ? | ? | ? | ? | 2 | 2 | 20
Seawater connection | ? | ? | ? | ? | ? | 2 | 2 | 61
Brine connection | ? | ? | ? | ? | ? | ? | ? | Yes
ISBL - Main packages
Enabling works | Mature | Contractor | Capacity | Low | Low | 5 | 5 | 110
Blue Hydrogen main process equipment | Immature | OEM | Capacity & Capability | High | High | Potential non UK supplier
CCS main process equipment | Immature | OEM | Capacity & Capability | High | High | Potential non UK supplier
Licensor | Immature | Technology /Licensor | Capacity & Capability | High | High | Limited supply chain
Major mechanical equipment | Mature | Supplier | Capacity | High | Medium | tbc | tbc | tbc
Minor mechanical equipment | Mature | Supplier | Capacity | Low | Low | TBC | TBC | Yes
Major E&ICA equipment | Mature | Supplier | Capacity | High | Medium | TBC | TBC | Yes
Bulk E&ICA equipment | Mature | Supplier | Capacity | Low | Low | TBC | TBC | Yes
PAU/PAR | Mature | Module/Fab | Capacity | High | High | TBC | TBC | Yes
Bulks - civils | Mature | Supplier | Capacity | Low | Low | TBC | TBC | Yes
Bulks - M&P | Mature | Supplier | Capacity | Low | Low | TBC | TBC | Yes
Bulks - E&I | Mature | Supplier | Capacity | Low | Low | TBC | TBC | Yes
Main Power & Control (including transformer) | Mature | OEM | Capacity & Capability | High | High | TBC | TBC | Yes
Main Control & Automation (Including DCS) | Mature | OEM | Capacity & Capability | High | High | TBC | TBC | Yes
Shipping (international) | Mature | Agent/ship | Capacity | Medium | Medium | TBC | TBC | Yes
Heavy lift & shift UK | Mature | Contractor | Capacity | Low | Low | TBC | TBC | Yes
Civil works (including structural & piling) | Mature | Contractor | Capacity | Medium | Low | TBC | TBC | Yes
Engineering Construction (M&E) | Mature | Contractor | Capacity | Medium | Low | TBC | TBC | Yes
Engineering Construction (AIP) | Mature | Contractor | Capacity | Medium | Low | TBC | TBC | Yes
Construction services, plant hire | Mature | Contractor | Capacity | Low | Low | TBC | Yes | Yes
CO2 Pipeline to terminal point including metering | Mature | Contractor/ Utility | Capacity | Low | TBC | TBC | Yes | Yes
H2 Pipeline to terminal point including metering | Mature | Contractor/ Utility | Capacity | Low | TBC | TBC | Yes | Yes
Commissioning/Ben ops trial | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
O&M contractor | TBC | TBC | TBC | TBC | TBC | 12 | 12 | 150
H2 Bacton - T&S
Booster/Compression (beach station/AGI)? | Mature | OEM | Capacity & Capability | High | High | TBC | TBC | Yes
Subsea pipe | Mature | Contractor | Capacity & Capability | TBC | TBC | TBC | TBC | Yes
Offshore injection (module, sea-bead) | Mature | Contractor | Capacity & Capability | TBC | TBC | TBC | TBC | Yes
H2 Pipeline to NTS | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Hydrogen storage | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Hydrogen loading/blending facility (AGI?) | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC
Rail loading facility (Hydrogen conversion)? | TBC | TBC | TBC | TBC | TBC | TBC | TBC | TBC

## Attach 3 timeline
Gated process
Stage gate process
|  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6
WBS element | Typical range (months) | Likely case | Launch | Identify & Initiate including options | Pre- FEED | Define & Plan FEED | Execute Design, Build & Commissioning | Completion & Commissioning (handover to operations) | Beneficial Operational trials | COD
Identify & Initiate including options | 6 to 24 | 18 | 2022 to Qtr 2 2023 | 2022 to Qtr 2 2023
Pre-FEED | 6 to 18 | 9 |  |  | Qtr. 2 2023 to Qtr. 4 2023
FEED | 9 to 18 | 12 |  |  | 6 months | Qtr. 1 2024 - Qtr. 4 2024
Contracting & procurement | 6 to 18 | 12 |  |  |  | 12 months | Qtr. 1 2025 to Qtr. 1 2028
TCPA Planning (if not a DCO) | 9 to 15 | 12 |  |  |  |  | 36 months |  | Qtr. 2 2028 | Mid 2028
DCO (assumed it will be a DCO) | 18-40 | 30 | [6 empty] | 3 months
Legal | 9 to 18 | 12 | 2022 to Qtr. 2 2024
Permitting | 18 to 36 | 24 |  |  | Qtr. 1 2025 - Qtr. 4 2025
Project funding? | 12 to 24 |  |  |  | 12 months | Qtr. 1 2026 to Qtr. 2 2027
EPC | 30 to 60 | 48 |  |  |  | 15 months | Qtr. 2 2027 to Qtr. 2 2032
EPC Engineering | 12 to 24 | 18 |  |  |  |  | 60 months |  | Qtr. 3 & 4 2032 | Start 2033
Long lead procurement | 9 to 36 | 24 | [6 empty] | 6 months
Construction | 18 to 36 | 24 | 2022 to Qtr. 2 2023
Commissioning | 6 to 18 | 12 |  |  | Qtr. 3 2023 - Qtr. 1 2024
Beneficial operation | 2 to 12 | 3 |  |  | 9 months | Qtr. 2 2024 - Qtr. 2 2025
[6 empty] | 12 months | Qtr. 3 2025 to Qtr. 1 2029
[7 empty] | 40 months |  | Qtr. 2 & 3 2029 | Qtr. 3 2029
6 months
FID
Scenario 1
optimistic
Scenario 2
pessimistic
Scenario 3
target
Planning & permitting
DCO or TCPA will also drive timeline if needed for FID
Engagement of consultants & Engineering contractors
General supply chain awareness, events & engagement
Engagement with Technology solution providers
Engage with good & service providers including construction companies